## Sheet1
[5 empty] | Planned |  |  | Actuals |  | Forecast
Request | Task ID | Step Description | Assigned to | Progress | Planned start date | Planned Duration | Planned Finish Date | Actual Start Date | Actual Completion Date | Forecast Completion Date
Graduate Recruitment | 1.1 | CV Screening | Resource 1 | In progress | 2023-02-27 | 9 | 2023-03-07 | 2023-02-27 | 2023-03-10 | 2023-03-08
Graduate Recruitment | 1.2 | 1st Stage Interview | Resource 1 | Not started | 2023-03-08 | 5 | 2023-03-12 |  |  | 1900-01-04
Graduate Recruitment | 1.3 | 2nd Stage Interview | Resource 1 | Not started | 2023-03-13 | 4 | 2023-03-16 |  |  | 1900-01-03
Graduate Recruitment | 1.4 | Issue Offers | Resource 1 | Not started | 2023-03-17 | 8 | 2023-03-24 |  |  | 1900-01-07
Graduate Recruitment | 1.5 | Onboard | Resource 1 | Not started | 2023-03-25 | 6 | 2023-03-30 |  |  | 1900-01-05
Experienced Recruitment | 2.1 | CV Screening | Resource 2 | In progress | 2023-02-27 | 5 | 2023-03-03 | 2023-02-28 |  | 2023-03-05
Experienced Recruitment | 2.2 | 1st Stage Interview | Resource 2 | Not started | 2023-03-04 | 10 | 2023-03-13 |  |  | 1900-01-09
Experienced Recruitment | 2.3 | 2nd Stage Interview | Resource 2 | Not started | 2023-03-14 | 0 | 2023-03-13 |  |  | 0
Experienced Recruitment | 2.4 | Issue Offers | Resource 2 | Not started | 2023-03-14 | 8 | 2023-03-21 |  |  | 1900-01-07
Experienced Recruitment | 2.5 | Onboard | Resource 2 | Not started | 2023-03-22 | 10 | 2023-03-31 |  |  | 1900-01-09
C-Suite Recruitment | 3.1 | CV Screening | Resource 3 | In progress | 2023-02-27 | 3 | 2023-03-01 | 2023-03-05 |  | 2023-03-08
C-Suite Recruitment | 3.2 | 1st Stage Interview | Resource 3 | Not started | 2023-03-02 | 2 | 2023-03-03 |  |  | 1900-01-01
C-Suite Recruitment | 3.3 | 2nd Stage Interview | Resource 4 | Not started | 2023-03-04 | 10 | 2023-03-13 |  |  | 1900-01-09
C-Suite Recruitment | 3.4 | Issue Offers | Resource 4 | Not started | 2023-03-14 | 8 | 2023-03-21 |  |  | 1900-01-07
C-Suite Recruitment | 3.5 | Onboard | Resource 4 | Not started | 2023-03-22 | 3 | 2023-03-24 |  |  | 1900-01-02
Formulas:
Planned Finish Date = Table1[[#This Row],[Planned start date]]+Table1[[#This Row],[Planned Duration]]-1
Forecast = Table1[[#This Row],[Actual Start Date]]+Table1[[#This Row],[Planned Duration]]
Planned = [Planned Finish Date, row above]+1