## Sheet1
[5 empty] | Planned |  |  | Actuals |  | Forecast
Request | Task ID | Step Description | Assigned to | Progress | Planned start date | Planned Duration | Planned Finish Date | Actual Start Date | Actual Completion Date | Forecast Completion Date
Graduate Recruitment | 1.1 | CV Screening | Resource 1 | In progress | 2023-02-27 | 9 | 2023-03-07 | 2023-02-27 | 2023-03-10 | 2023-03-10
Graduate Recruitment | 1.2 | 1st Stage Interview | Resource 1 | Not started | 2023-03-08 | 5 | 2023-03-12 | 2023-03-11 |  | 2023-03-16
Graduate Recruitment | 1.3 | 2nd Stage Interview | Resource 1 | Not started | 2023-03-13 | 4 | 2023-03-16 |  |  | 2023-03-16
Graduate Recruitment | 1.4 | Issue Offers | Resource 1 | Not started | 2023-03-17 | 8 | 2023-03-24 |  |  | 2023-03-24
Graduate Recruitment | 1.5 | Onboard | Resource 1 | Not started | 2023-03-25 | 6 | 2023-03-30 |  |  | 2023-03-30
Experienced Recruitment | 2.1 | CV Screening | Resource 2 | In progress | 2023-02-27 | 5 | 2023-03-03 | 2023-02-28 | 2023-03-03 | 2023-03-03
Experienced Recruitment | 2.2 | 1st Stage Interview | Resource 2 | Not started | 2023-03-04 | 10 | 2023-03-13 |  |  | 2023-03-13
Experienced Recruitment | 2.3 | 2nd Stage Interview | Resource 2 | Not started | 2023-03-14 | 0 | 2023-03-13 |  |  | 2023-03-13
Experienced Recruitment | 2.4 | Issue Offers | Resource 2 | Not started | 2023-03-14 | 8 | 2023-03-21 |  |  | 2023-03-21
Experienced Recruitment | 2.5 | Onboard | Resource 2 | Not started | 2023-03-22 | 10 | 2023-03-31 |  |  | 2023-03-31
C-Suite Recruitment | 3.1 | CV Screening | Resource 3 | In progress | 2023-02-27 | 3 | 2023-03-01 | 2023-03-05 |  | 2023-03-08
C-Suite Recruitment | 3.2 | 1st Stage Interview | Resource 3 | Not started | 2023-03-02 | 2 | 2023-03-03 |  |  | 2023-03-03
C-Suite Recruitment | 3.3 | 2nd Stage Interview | Resource 4 | Not started | 2023-03-04 | 10 | 2023-03-13 |  |  | 2023-03-13
C-Suite Recruitment | 3.4 | Issue Offers | Resource 4 | Not started | 2023-03-14 | 8 | 2023-03-21 |  |  | 2023-03-21
C-Suite Recruitment | 3.5 | Onboard | Resource 4 | Not started | 2023-03-22 | 3 | 2023-03-24 |  |  | 2023-03-24
Formulas:
Planned Finish Date = Sheet1!$[Planned]+Sheet1!$[Planned Duration]-1
Forecast = IFS(Sheet1!$[Actual Completion Date]<>"", Table2[[#This Row],[Actual Completion Date]], Sheet1!$[Actuals]<>"", Sheet1!$[Actuals]+Sheet1!$[Planned Duration], Sheet1!$[Actual Completion Date]="", Sheet1!$[Planned Finish Date])
Planned = [Planned Finish Date, row above]+1
Actuals = [Actual Completion Date, row above]+1

## Data
| Duration | 0 | 5 | 3 | 2 | 2
Task | Title | Receive request | Formal Paperwork Raised | Request approved | Sent to actioning party | Actioning party accepts
1.1 | Plan | 2022-05-01 | 2022-05-06 | 2022-05-09 | 2022-05-11 | 2022-05-13
Graduate Recruitment | Actual | 2022-05-02 | 2022-05-07
| Forecast |  |  | 2022-05-10 | 2022-05-12 | 2022-05-14
| Plan | 2022-05-01 | 2144-09-16 | 2267-02-05 | 2389-06-28 | 223489
Experienced Recruitment | Actual | 2022-05-04
| Forecast |  | 2022-05-10 | 2022-05-13 | 2022-05-15 | 2022-05-17
| Plan | 2022-05-12 | 2022-05-17 | 2022-05-20 | 2022-05-22 | 2022-05-24
C-Suite Recruitment | Actual
| Forecast | 2022-05-12 | 2022-05-17 | 2022-05-20 | 2022-05-22 | 2022-05-24
Formulas:
Formal Paperwork Raised = [Receive request]+E2
Request approved = [Formal Paperwork Raised]+F2
Sent to actioning party = [Request approved]+G2
Actioning party accepts = [Sent to actioning party]+H2